## 3.2 Project Gantt Chart
Task / Deliverable | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Project Initiation & Planning | bar: W1 to W3
GitHub Repository Setup | bar: W1 to W2
Assessment 1: Proposal + ILP | bar: W1 to W4
Stakeholder Interview Plan | bar: W3 to W4
Conduct Stakeholder Interviews | bar: W4 to W5
Cloud Security Architecture Review | bar: W4 to W6
Risk Assessment Table | bar: W5 to W6
Progress Report 1 ← due W6 | bar: W6
Security Posture Report | bar: W7 to W8
Risk Assessment Report | bar: W7 to W8
Security Policies Pack | bar: W8 to W9
Progress Report 2 ← due W9 | bar: W9
Remediation & Recommendations Report | bar: W10 to W11
Final Report Compilation & Review | bar: W11 to W12
Final Report Submission (8 Jun) | bar: W13
Final Presentation (9 Jun) | bar: W13
NOTES: