## Gantt Chart
MediCare Plus Clinic — Network Security Assessment
Project Gantt Chart ¦ Updated: End of Week 7 — April 2026 ¦ Project Leader: Carlos Gomez Mendez
# | Task | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | Status | Progress | Notes
1 | Project Initiation & Planning | ALL | [13 empty] | COMPLETE | 100% | Scope, roles, mentor confirmed
2 | GitHub Repository Setup | Carlos | [13 empty] | COMPLETE | 100% | Repo created, all members onboarded
3 | Group Project Proposal + ILP | ALL | [13 empty] | COMPLETE | 100% | 10.5/12 received Wk 6
4 | Stakeholder Interview Plan | Abdullah | [13 empty] | COMPLETE | 100% | 27 questions across 6 domains
5 | Conduct Stakeholder Interviews | Abdullah | [13 empty] | COMPLETE | 100% | 3 stakeholders (David, Sarah, Maria)
6 | System Architecture Diagram | Kishan | [13 empty] | COMPLETE | 100% | Delivered Wk 7 — IPs, subnets, F1-F7 mapped
7 | Cloud Security Architecture Review | Kishan | [13 empty] | IN PROGRESS | 60% | Diagram done; writeup waiting on Kishan
8 | Risk Assessment Table | Abdullah | [13 empty] | IN PROGRESS | 50% | v2 has 12 risks; needs ISM/NIST mapping + R13-R16
9 | Azure Evidence Capture (CQU tenant) | Carlos | [13 empty] | COMPLETE | 100% | 14 screenshots captured Wk 7 covering F1-F7
10 | Progress Report 1 (12.5%) | Individual | [13 empty] | COMPLETE | 100% | Submitted Wk 6
11 | Security Posture Report | Carlos | [13 empty] | IN PROGRESS | 75% | Sec 1, 2, 3, 5 written; Sec 4 narrative + Sec 6 pending team
12 | Risk Assessment Report | Abdullah | [13 empty] | NOT STARTED | 10% | Outline only; depends on finalised risk table
13 | Security Policies Pack | Kishan | [13 empty] | NOT STARTED | 5% | Research phase only
14 | Progress Report 2 (12.5%) | Individual | [13 empty] | DUE WEEK 9 | 0% | Each member submits individually
15 | Remediation & Recommendations Report | Carlos | [13 empty] | NOT STARTED | 0% | Wk 9-10 (compressed per Azmat feedback)
16 | Final Report Compilation | ALL | [13 empty] | NOT STARTED | 0% | Wk 10-11; integrate all artefacts
17 | Group Presentation Prep | ALL | [13 empty] | NOT STARTED | 0% | Slides + rehearsal Wk 11-12
18 | Final Report Submission (40%) | ALL | [13 empty] | DUE 8 JUN | 0% | Mon 8 Jun — 11:45pm AEST
19 | Final Presentation (10%) | ALL | [13 empty] | DUE 9 JUN | 0% | Tue 9 Jun
20 | Individual Reflection (5%) | Individual | [13 empty] | DUE 9 JUN | 0% | Tue 9 Jun
Legend: |  | Complete |  | In Progress |  | Planned / Upcoming |  | Overdue / At Risk
Week 7 Status Update (April 2026)
✓ Architecture Diagram: Delivered by Kishan (3 weeks late, but final version is good — IP ranges, subnets, F1-F7 markers)
✓ Azure Evidence: 14 screenshots captured by Carlos covering all 7 cloud findings (F1-F7)
✓ Security Posture Report: 75% complete (Sec 1, 2, 3, 5 written using captured evidence)
⚠ Cloud Security Review writeup: Kishan diagram done, full writeup pending — Carlos has backup version ready
⚠ Risk Assessment Table: Stuck at 12 risks (v2 from Wk 5). Needs ISM/NIST mapping and R13-R16. No update from Abdullah since Wk 6.
→ Next: Mentor meeting Thursday 11am. Push Kishan and Abdullah for written deliverables before Wk 8.
→ Compressed timeline (per Azmat Wk 6 feedback): All technical work must be complete by end of Wk 11.