## Gantt Chart
MediCare Plus Clinic — Network Security Assessment
Project Gantt Chart ¦ Updated: End of Week 8 — May 2026 ¦ Project Leader: Carlos Gomez Mendez
# | Task | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | Status | Progress | Notes
1 | Project Initiation & Planning | ALL | [13 empty] | COMPLETE | 100% | Scope, roles, mentor confirmed
2 | GitHub Repository Setup | Carlos | [13 empty] | COMPLETE | 100% | Repo active, multiple commits weekly
3 | Group Project Proposal + ILP | ALL | [13 empty] | COMPLETE | 100% | Submitted Wk 5. Mark: 10.5/12 (87.5%)
4 | Stakeholder Interview Plan | Abdullah | [13 empty] | COMPLETE | 100% | 27 questions across 6 domains
5 | Conduct Stakeholder Interviews | Abdullah | [13 empty] | COMPLETE | 100% | 3 stakeholders interviewed (David, Sarah, Maria)
6 | System Architecture Diagram (Current) | Kishan | [13 empty] | COMPLETE | 100% | Delivered Wk 7. Includes IPs, subnets, F1-F7 markers
7 | Risk Assessment Table (18 risks) | Abdullah | [13 empty] | COMPLETE | 100% | 18 risks, ISM + NIST mapping, MITRE ATT&CK refs
8 | Risk Assessment Report (narrative) | Abdullah | [13 empty] | COMPLETE | 100% | 1,908 words delivered Wk 8. Pending: R08/R12/R13 narratives + refs
9 | Azure Evidence Capture (14 SS) | Carlos | [13 empty] | COMPLETE | 100% | 14 screenshots covering F1-F7. Committed to GitHub
10 | Target State Architecture Diagram | Carlos | [13 empty] | COMPLETE | 100% | Built Wk 7 per Azmat feedback. HTML/SVG
11 | Progress Report 1 (12.5%) | Individual | [13 empty] | COMPLETE | 100% | Submitted Wk 6. Mark: 11/12.5 (91.67%)
12 | Cloud Security Architecture Review | Kishan | [13 empty] | COMPLETE | 100% | Carlos draft sent. Kishan adding screenshots + arrows. v2 expected EOW 8
13 | Security Posture Report | Carlos | [13 empty] | IN PROGRESS | 80% | Sec 1,2,3,5,6 done. Sec 4 narrative pending. ZERO AI risk
14 | Action Plan for Kishan (Cloud Review) | Carlos | [13 empty] | COMPLETE | 100% | Step-by-step instructions sent Wk 8 to support delivery
15 | Progress Report 2 (12.5%) | Individual | [13 empty] | DUE MON 12 MAY | 95% | Drafted. Submitting Sun 10 May night
16 | Security Policies Pack | Kishan | [13 empty] | NOT STARTED | 0% | Owed for Final Report. Target: Wk 9-10
17 | Remediation & Recommendations Report | Carlos | [13 empty] | NOT STARTED | 5% | Begin Wk 9. Outline ready. Target completion: Wk 10
18 | Final Report Compilation | ALL | [13 empty] | NOT STARTED | 0% | Wk 10-11. Compressed per Azmat feedback
19 | Group Presentation Prep | ALL | [13 empty] | NOT STARTED | 0% | Slides + rehearsal Wk 11-12
20 | Final Report Submission (40%) | ALL | [13 empty] | DUE 8 JUN | 0% | Mon 8 June 2026 — 11:45pm AEST
21 | Final Presentation (10%) | ALL | [13 empty] | DUE 9 JUN | 0% | Tue 9 June 2026
22 | Individual Reflection (5%) | Individual | [13 empty] | DUE 9 JUN | 0% | Tue 9 June 2026
Legend: |  | Complete |  | In Progress |  | Planned / Upcoming |  | Overdue / At Risk
Week 8 Status Update (May 2026)
✓ Risk Assessment Report: Delivered by Abdullah (1,908 words). NIST 800-30, ISM/NIST mapping, MITRE ATT&CK references, OAIC/ACSC threat data
✓ Azure Evidence Capture: 14 screenshots committed by Carlos, covering all 7 cloud findings (F1-F7)
✓ Target State Architecture Diagram: Built by Carlos per Azmat's Week 7 feedback. Pairs with Kishan's current-state diagram
✓ Cloud Security Review draft: Carlos drafted (3,671 words). Sent to Kishan with action plan for finalisation
✓ Security Posture Report: 80% complete (Sec 1,2,3,5,6 done with ZERO AI flags). Section 4 narrative pending
⚠ Cloud Security Review v2: Kishan owes screenshots embedded + diagram arrows update. Target: end of Week 8
⚠ Kishan absent from Week 8 mentor meeting. Carlos followed up via Teams with meeting outcomes
→ Azmat's Week 9 directive: 'Show ONLY technical progress next week, not reports' — each member prepares hands-on demo
→ Progress Report 2 due Monday 12 May (drafted, submitting Sunday night)
→ Week 9 focus: Begin Remediation & Recommendations Report. Prepare Azure portal demo for mentor meeting
→ Compressed timeline holds: All technical work complete by Week 11. Wk 12-13 = compilation + presentation only